FPMC · PRODUCTION

Launch Orchestration

Radi x FPMC — Release, Brand Launch, Social & Website

Workstreams · Deadlines · Agents & Automations · Workflows · Checklists

As of: 05.07.2026 · v6 (final — incl. batch review & audio QA) · Confidential — internal use only

# 0. Summary & Goals

The Radi project is FPMC's public brand launch. Goal of this orchestration: deliver the music video on time (8 Jul), build the public FPMC presence in parallel (social + Launch Slice website), and roll out the release with a staged hype campaign that generates reach and first revenue paths (giveaway → email list → later offers).

- Hard date: music video handover to Radi on 8 July 2026.

- Release date LOCKED: Friday, 24 July 2026 — confirmed via WhatsApp on 4 July (screenshot in 00_Intake).

- FPMC Legacy (full platform P0–P6) continues unchanged; only the Launch Slice is built for this launch.

Ground rule: No step without backup (3-2-1). Nothing FPMC-owned goes public before Radi's 7-day review window has expired or his written approval is in.

# 1. Timeline & Milestones

| Date | Milestone | Owner | Status |
| --- | --- | --- | --- |
| 4 Jul | Release date locked with Radi (24 Jul); addenda + schedule sent | Hazem / Saeed | done |
| 3–7 Jul | Delivery sprint: final MV edit, QA, export formats | Saeed + Dilara | running |
| 5–6 Jul | Secure social handles, set up profiles, configure schedulers | Hazem | running |
| 6–15 Jul | WS2 assets: logo variants, banners, watermark, Higgsfield loops, logo sting | Hazem | open |
| 5–12 Jul | Build & launch the Launch Slice website (incl. /links) | Hazem + Claude Code | open |
| 8 Jul | MV handover to Radi (MV + reels only) | Saeed | hard |
| 8–13 Jul | BTS/podcast edit runs in parallel; audio correction mix + master (podcast, BTS if needed) | Saeed + Dilara / audio: Jasper | open |
| 9 Jul | Review link BATCH 1 (teaser/BTS snippets) to Radi — window runs out, cleared 16 Jul | Saeed | hard |
| 14 Jul | Review link BATCH 2 (podcast episode, BTS long-form) — cleared 21 Jul | Saeed | hard |
| 9–21 Jul | Radi batch reviews (7 days each from link); actively request early approval via WhatsApp | external | blocker |
| 8–15 Jul | WS4 (pulled forward, critical): teasers, podcast edit & trailer, produce all content | team | open |
| 15 Jul | Everything scheduled, QA gate passed, full backup | Dilara (QA) | hard |
| 16–18 Jul | Phase 1 · Tease | Hazem | planned |
| 19–21 Jul | Phase 2 · Reveal | Hazem | planned |
| 22–23 Jul | Phase 3 · Countdown (date announce, merch reveal, Premiere) | Hazem | planned |
| 24 Jul | RELEASE: MV Premiere 18:00, cross-posting, giveaway start | all | hard |
| 27–29 Jul | Publish podcast episode + start clip pipeline | Saeed + Dilara (audio: Jasper) | planned |
| Aug | BTS long-form, winner announce, FPMC Music debut (track + session video) | Jasper + Hazem | planned |

Dependencies (waiting on Radi): 1) Warner logo file (blocks the final export!), 2) both signed addenda, 3) “confirmed” on the call summary, 4) review approval (target 12 Jul). Release date is locked.

# 2. Workstreams in Detail

## WS1 — Delivery Sprint (critical path)

- Finalize MV edit; QA: picture, sound, color grade, spelling in credits.

- Verify credits: “FPMC – Film Production Music Club” as Executive Producer in on-screen credits (contractual).

- Hold the final export until the Warner logo OK arrives — one render, not two.

- Export matrix: 16:9 master (broadcast), 9:16 + 1:1 social cuts, thumbnails.

- Handover on 8 Jul: MV + reels only. The documentary content is still in the edit at that point.

- Batch review instead of a single link (contract §6, window per material sent): batch 1 (teaser/BTS snippets) by 9 Jul → cleared 16 Jul; batch 2 (podcast episode + BTS long-form) by 14 Jul → cleared 21 Jul.

Backup: Raw footage + project files to 04_Media + cloud + Datentresor (3-2-1), before handover.

## WS2 — Social Foundation

- Secure handles: YouTube, Instagram, TikTok (+ X optional) — consistent @fpmc naming.

- Profiles in Lichtspiel style: achromatic, Cinzel wordmark, clear bio (DE/EN), link to the Launch Slice.

- Connect Meta Business Suite (IG+FB), activate TikTok scheduler, set up YouTube channel layout (banner, trailer placeholder).

- Prepare community rules & reply snippets (DE/EN/AR) for comments.

- Asset production from the original logo (print version in 04_Marke_FPMC): profile-picture crops (tested square + round), void-black version, small wordmark, subtle video watermark for all clips.

- Static assets: YouTube banner (2560×1440, safe zone), IG/TikTok profile pictures, story/post templates, thumbnail template, end card.

- Higgsfield assets: logo motion loops (master prompt 3.5) for website hero + tease phase, channel trailer loop, animated logo sting (2–3s) as intro/outro for all videos.

WS2 asset deadline: All assets done and versioned in 04_Marke_FPMC by 15 July — every teaser needs watermark + sting.

## WS3 — Launch Slice Website

- One cinematic page (Lichtspiel v2): Radi project hub, embedded YouTube, email capture (double opt-in), giveaway section (hidden until cleared), Impressum/privacy.

- Built via Claude Code from the existing kit (CLAUDE.md, BUILD-SESSION-KICKOFF.md) by Hazem; review via the QA gate (Dilara + a second person).

- /links route on own domain as link-in-bio (Lichtspiel style, GDPR-clean, no third-party tracking); Linktree only as fallback if the Slice slips.

- Transactional email via branded domain (no sandbox sender) — the engineering-handoff standard applies from day one.

- GDPR: double opt-in for the list, privacy policy, build cookie-light (no unnecessary tracking).

Non-goal: No shop, no login, no platform features — those stay in the P0–P6 Legacy roadmap.

## WS4 — Content & Teaser Production (PULLED FORWARD: 8–15 Jul — critical)

- Cut 5–10s silent teasers from BTS (“something is coming”, no context) — may only go live after review clearance.

- BTS/podcast edit continues in parallel with the delivery sprint (8–13 Jul) — owners: Saeed + Dilara.

- Audio QA by Jasper: correct mix + master of the podcast episode, check BTS sound and fix where needed — before each review batch goes out.

- Podcast: edit the episode, trailer (30–60s), audiogram snippets.

- Lock the story angle: the DACH ↔ MENA bridge — a Tunisian rap star in Cologne. Strongest narrative, run it consistently.

- Hard deadline: ALL tease/reveal/countdown content produced, QA-checked and scheduled by 15 July — from 16 July we only publish, we no longer produce.

## WS5 — Giveaway & Merch (blocked until addendum signed)

- Draft the terms & conditions (GDPR-compliant) now, publish later: organizer, period, participation, prize, exclusions, data processing.

- Design merch → express approval by Radi per design (addendum §3).

- No album/Warner branding on merch without written clearance from the rights holder (addendum §4).

- Logistics: small run via print-on-demand; document shipping to winners.

# 3. Roles & Responsibilities

| Role | Responsibility in the launch |
| --- | --- |
| Hazem (EP) | AI & marketing specialist: campaign lead, content creation & social media, monetization (YouTube Partner Program, podcast distribution, analytics), automations, website build (Claude Code) — assisted by Dilara & Jasper. Drafts the Radi/Warner communication. |
| Saeed | MV & podcast production (with Dilara), delivery. Owner of the Radi/Warner relationship: sends & signs (drafts by Hazem). Arabic-language content. |
| Dilara | MV & podcast production (with Saeed). Finance/receipts, giveaway handling. Owner of QA & data backup (3-2-1 checks per gate). |
| Jasper | All audio: mix, master, podcast sound, sound design. Audio correction podcast + BTS if needed during the delivery window (before each review batch). FPMC Music label buildout: distribution, releases, split sheets, royalty handling — his specialty. |

Four-eyes principle: Every publication (video, post, page) is approved by at least two people; nothing goes live without EP sign-off. QA gate owner: Dilara + one rotating second.

# 4. Agents, Automations & Tools

## 4.1 Tool Matrix

| Tool / Agent | Use | Owner / Note |
| --- | --- | --- |
| Claude Code | Launch Slice build, automation scripts, docs | Entry via CLAUDE.md + kickoff doc |
| Claude (chat) | Copy, DE/EN/AR translation, planning, documents | Use master prompts from the workflow playbook |
| Higgsfield – Personal Clipper | YouTube long-form → automatic 9:16 clips with subtitles | Clip podcast & studio session after upload |
| Higgsfield – Virality Predictor | Check teasers/clips before publishing | Post only the best 2–3 variants |
| Higgsfield – Dubbing | Sync podcast/clips AR ↔ DE ↔ EN | Serve both markets (DACH + MENA) |
| Higgsfield – Upscale/Reframe | Format change 16:9 → 9:16, quality lift | For social cuts from the master |
| Higgsfield – Motion loops | Cinematic loops for website & tease phase | Master prompt 3.5; brand signature |
| Meta Business Suite | IG/FB planning, posting automation | Load the calendar in one sitting |
| TikTok Scheduler | TikTok planning | Use native scheduling |
| YouTube Studio | Premiere feature, end cards, chapters | Premiere = built-in countdown |
| Email (branded domain) | Double opt-in, launch mail, winner notification | No sandbox sender |
| Git + Datentresor | Versioning, 3-2-1 backups, restore tests | Standard per the data-backup playbook |

## 4.2 Automated Workflows (Pipelines)

Repeatable chains — set up once, run per asset:

- Clip pipeline: Long-form on YouTube (unlisted) → Personal Clipper (n clips, 9:16, brand-matching subtitle font) → Virality Predictor → schedule the top clips → document result links in the calendar.

- Language pipeline: Final clip → dubbing (AR/DE/EN) → QA by native speakers on the team (Saeed AR, Hazem AR/NL, Jasper FR) → market-split distribution (DACH accounts vs. MENA delivery).

- Website pipeline: Claude Code session per kickoff doc → branch + commit per building block → review via QA gate (Dilara + second person) → deploy → tag → full backup (P6 discipline also for the Slice).

- Lead pipeline: Email capture on the Slice → double-opt-in mail → segment “Radi Launch” → later migration into the Legacy platform (schema is prepared for it).

- Backup pipeline: After every render/edit session: 04_Media + cloud; weekly Datentresor sync; before release full backup + tag “release”.

## 4.3 AI Agent on the Website (optional, phase 2)

The digital reception in the brand voice (master prompt 3.6) does not go into the Launch Slice — only once the Slice is live and the campaign is running. Reason: no additional QA load on the critical path.

# 5. Content Types & Hype Ladder

| Phase | Content | Formats | Frequency |
| --- | --- | --- | --- |
| 1 · Tease (16–18 Jul) | Silent 5–10s snippets, cinematic, no context | Reels/TikTok/Shorts | daily |
| 2 · Reveal (19–21 Jul) | BTS drops, studio moments, DACH↔MENA story | Reels + carousels + stories | daily |
| 3 · Countdown (22–23 Jul) | Date announce, podcast trailer, merch reveal + giveaway announce, YouTube Premiere | all channels | daily |
| 4 · Release (24 Jul) | MV Premiere 18:00, cross-posting with Radi (credit/tag contractual), giveaway start | YouTube + all | release day |
| 5 · Sustain (from 27 Jul) | Podcast episode 27–29 Jul, BTS long-form, FPMC Music debut (studio track + session video), winner announce | YouTube + clips + DSPs | 2–4 weeks |

- Every phase feeds the email list: CTA in bio/end card always points to the Launch Slice.

- Think bilingual: core posts DE/EN, MENA delivery in AR (language pipeline).

- Radi shares FPMC content on his channels with credit (contract §6) — actively request it, deliver ready-made assets.

- Monetization (Hazem): prepare YouTube Partner Program, set up podcast distribution (Spotify etc.), document analytics per channel — assuming Content ID clarity with Warner.

# 6. Content Calendar (16–24 Jul)

Gate: Every post requires clearance of its review batch: tease/reveal material cleared from 16 Jul (batch 1), podcast/long-form from 21 Jul (batch 2). All content scheduled by 15 Jul; per-post sign-off via the QA gate (Dilara + second person).

| Day | Content | Channels | Owner |
| --- | --- | --- | --- |
| Thu 16 Jul | Tease 1: snippet A (silent, cinematic, no context), 18:00 · bios + /links live | Reels, TikTok, Shorts | Hazem |
| Fri 17 Jul | Tease 2: snippet B + story series (3 frames) | Reels, TikTok, Shorts, story | Hazem |
| Sat 18 Jul | Tease 3: snippet C + active community engagement in comments | all | Hazem |
| Sun 19 Jul | Reveal 1: BTS drop arrival/studio + story Tunisia→Cologne part 1 | Reels + story | Hazem |
| Mon 20 Jul | Reveal 2: studio moments + story carousel; request Radi repost (deliver assets) | Reels, carousel | Hazem / Saeed |
| Tue 21 Jul | Reveal 3: BTS + first podcast hint | Reels, TikTok | Hazem |
| Wed 22 Jul | Countdown 1: date announce + create YouTube Premiere + podcast trailer | all + YouTube | Hazem |
| Thu 23 Jul | Countdown 2: merch reveal + giveaway announcement (T&C live!), Premiere reminder | all | Hazem / Dilara |
| Fri 24 Jul | RELEASE: Premiere 18:00 · cross-posting both sides · giveaway opens · community shift until 22:00 | YouTube + all | all |
| Sat–Sun 25–26 Jul | MV clips, reshare reactions, push the giveaway | Reels, TikTok, Shorts | Hazem |
| Mon–Wed 27–29 Jul | Podcast episode live + clip pipeline (Personal Clipper → Virality → scheduler) | YouTube + clips | Saeed + Dilara |

- Posting times: 18:00–19:00 CEST as default (German after-work, 17:00–18:00 Tunis) — adjust after first analytics.

- MENA delivery: AR versions of core posts via the language pipeline, time-shifted the same day.

# 7. Checklists

## Before handover (8 Jul)

- MV final, QA by two people, credits verified (EP credit).

- Warner logo placed (if OK received) — otherwise document handover without logo.

- Raw footage + project backed up (3-2-1), export matrix filed.

- Batch-1 review link (teaser/BTS snippets) to Radi by 9 Jul at the latest; batch 2 by 14 Jul — deadlines noted.

## Before the first public post (16 Jul)

- Batch-1 window expired (16 Jul) or written early approval from Radi.

- Song-rights confirmation email filed in the Datentresor.

- Social profiles complete, link to Slice active, Impressum reachable.

- No Warner reference in own marketing without written OK.

## Before giveaway announcement (23 Jul)

- Merch addendum signed by Radi; designs expressly approved.

- Terms & conditions + privacy notices online.

- Double-opt-in flow tested.

## Before release (24 Jul)

- Content ID whitelisting for FPMC channels confirmed (via Radi/Warner).

- Calendar fully loaded (all channels), YouTube Premiere scheduled.

- Full backup + tag “release”.

Confidential · internal use only · FPMC · Launch Orchestration v6 · 05.07.2026